## Issues
TROLL issue and bug tracker
Date | TROLL version | Type of issue | Location in TROLL (line or function) | Issue | Reported by | Status | Date of Solution/ Rejection | Comment to Solution/ Rejection
2017-01-15 | 2.3 | Readability | UpdateTree() | Naming convention for counting in loops (iii, i,…)? | FF | Unsolved
2017-01-15 | 2.3 | CriticalUpdate | UpdateSeed() | Within UpdateSeed(), removed checking for T[site].t_age>0. Setting the seed counter s_Seed[site] to zero in this case will be done earlier in UpdateTree(). Or could potentially be eliminated, as it is quite costly from a performance point of view. | FF | Unsolved
2017-01-15 | 2.3 | Structure | Tree::Growth() and | Inconsistency in calculations: The final biomass is computed with a different biomass equation than the one used for allocation of biomass in growth | FF | Unsolved
2017-01-15 | 2.3 | Readability | Tree::Growth() | Uncommented lines for negative t_NPP: t_NPP=t_GPP- 1.5*(t_Rday+t_Rnight) - 1.50*t_Rstem; | FF | Unsolved
2017-01-15 | 2.3 | Readability | AllocMem() | Uncommented lines that compute SBORD etc. | FF | Unsolved
2017-01-15 | 2.3 | Suggestion | UpdateField(), OutputField() | Right now, LAI3D is updated at every time step for every layer between 0 and HEIGHT. Maybe just update till height of heighest tree at the moment. Same for layer(h) | FF | Unsolved
2017-01-16 | 2.3 | Suggestion | CalcLAI() | compute contributions for crown_top and crown_base in advance (performance benefit for large trees?) | FF | Unsolved
2017-01-16 | 2.3 | Suggestion | Tree::Growth() and dailyGPPleaf() | Going local: examine potential performance speedup by removing constant referral to global array PPFD_daily[24] etc. in dailyGPPleaf() --> would need reworking of code, i.e. centralised calculation of GPP | FF | Unsolved
2017-01-16 | 2.3 | Suggestion | General | When diameter exceeds grid size, we should implement effect on surroundings, no? | FF | Unsolved
2017-01-16 | 2.3 | Bug | UpdateSeed() | Update for simple seed function (without seedtradeoff) has updated the age of seeds regardless of whether seeds were present or not (s_Seed[site]=0). This led to the constant creation of seeds independent from other sources (metacommunity, mother trees), and in consquence to a very homogeneous seedbank, a constant presence of all species and little influence of initial parameters | FF | Solved | 2017-01-16 | Bug confirmed by IM. Currently being checked for consequences on forest dynamics.
2017-01-16 | 2.3 | Suggestion | CalcLAI() | Add LAI that is result of branches and stem (to convert LAD to PAD) | FF | Unsolved

## Meta
Issue type | Status
Bug | Solved
Structure | Unsolved
Inefficiency | Rejected
CriticalUpdate
Suggestion
Readability